## Sheet1
jira:ticket	core:name	jira:status	jira:storypoints	jira:depends-on	jira:team	jira:ticket-type	jira:feature	jira:sprint	jira:release
TQC-10348	Add flux field parameters	closed	8		Datastore	Story	Flux Compensation	2020-05	1.2
TQC-10349	Flux calculation	in validation	20	TQC-10348	Simulation	Story	Flux Compensation	2020-06	1.2
TQC-10350	Add Flux to UI	in progress	10	TQC-10348+TQC-10351+TQC-10353	Frontend	Story	Flux Compensation	2020-06	1.2
TQC-10351	Flux support	in code review	8	TQC-10348	Platform	Story	Flux Compensation	2020-06	1.2
TQC-10352	Flux analytics	in progress	14	TQC-10348+TQC-10350	Analytics	Story	Flux Compensation	2020-06	1.2
TQC-10353	Flux workflow	open	10	TQC-10348	Workflow	Story	Flux Compensation	2020-08	1.3
TQC-10354	Full fluxination	open	20	TQC-10348+TQC-10349	Simulation	Story	Flux Compensation	2020-11	1.3
TQC-10355	Hubble data schema	closed	6		Datastore	Story	Hubble Data Import	2020-05	1.2
TQC-10356	Constellation influence	in validation	8	TQC-10355	Simulation	Story	Hubble Data Import	2020-06	1.2
TQC-10357	Hubble import connector	in validation	4	TQC-10355	Datastore	Story	Hubble Data Import	2020-06	1.2
TQC-10358	Hubble connectivity	in code review	4		Platform	Story	Hubble Data Import	2020-06	1.2
TQC-10359	Astrology module	open	14	TQC-10357+TQC-10358	Analytics	Story	Hubble Data Import	2020-12	1.3
TQC-10360	Quantum bit storage	closed	20		Datastore	Story	Fuzzy data support	2020-06	1.3
TQC-10361	Oscillation simulation	blocked	10	TQC-10365+TQC-10360	Simulation	Story	Fuzzy data support	2020-07	1.3
TQC-10362	Blur mode for UI	in progress	5		Frontend	Story	Fuzzy data support	2020-07	1.3
TQC-10363	Nondeterministic load distribution	in progress	6	TQC-10351	Platform	Story	Fuzzy data support	2020-07	1.3
TQC-10364	Add probability functions	in code review	10	TQC-10360	Analytics	Story	Fuzzy data support	2020-07	1.3
TQC-10365	Extract probabilities	open	8	TQC-10360+TQC-10354	Simulation	Story	Fuzzy data support	2020-08	1.3
TQC-10366	Add tweet buttons	open	2		Frontend	Story	Twitter integration	2020-09	1.3
TQC-10367	Tweet overview	open	6		Frontend	Story	Twitter integration	2020-09	1.3
TQC-10368	Tweet approval workflow	open	8		Workflow	Story	Twitter integration	2020-10	1.3
TQC-10369	Tweet deletion workflow	open	6		Workflow	Story	Twitter integration	2020-10	1.3
TQC-10370	Twitter connectivity	open	10		Platform	Story	Twitter integration	2020-09	1.3
TQC-10371	NLP framework evaluation	open	6		Analytics	Spike	Chatbot		1.3
TQC-10372	NLP queries	open	16	TQC-10371+TQC-10373	Analytics	Story	Chatbot		1.3
TQC-10373	Entity catalog	open	10		Platform	Story	Chatbot		1.3
TQC-10374	Redesign Analytic Layout	open	4		Frontend	Story	Chatbot		1.3
TQC-10375	Chat Column	open	6		Frontend	Story	Chatbot		1.3
TQC-10376	Embed visualizations in chat	open	6	TQC-10375	Frontend	Story	Chatbot		1.3
TQC-10377	Add spin fields to schema	open	4		Datastore	Story	Spin simulation		1.3
TQC-10378	Spin approximation algorithm	open	18	TQC-10359	Simulation	Story	Spin simulation		1.3
TQC-10379	Embed spin in flux	open	10	TQC-10378+TQC-10348	Simulation	Story	Spin simulation		1.3
TQC-10380	Embed spin in analytics	open	8	TQC-10378	Analytics	Story	Spin simulation		1.3
TQC-10381	Design spin viz	open	10		Frontend	Story	Spin simulation		1.3
TQC-10382	Implement spin viz	open	10	TQC-10381+TQC-10380	Frontend	Story	Spin simulation		1.3
TQC-10383	Location service selection	open	4		Platform	Spike	Location awareness		1.3
TQC-10384	Location service connectivity	open	6	TQC-10383	Platform	Story	Location awareness		1.3
TQC-10385	Location-sensitive model	open	10	TQC-10384	Simulation	Story	Location awareness		1.3
TQC-10386	Geospatial results	open	8	TQC-10385+TQC-10384	Simulation	Story	Location awareness		1.3
TQC-10387	Location in UI	open	8	TQC-10386+TQC-10384	Frontend	Story	Location awareness		1.3
TQC-10388	Set up AWS clusters	open	4		Platform	Story	Distributed calculation		1.4
TQC-10389	Deployment scripts	open	10		Platform	Story	Distributed calculation		1.4
TQC-10390	Mesos enabling	open	20	TQC-10388+TQC-10389	Simulation	Story	Distributed calculation		1.4
TQC-10391	Calculation Partitioning	open	20	TQC-10390	Simulation	Story	Distributed calculation		1.4
TQC-10392	Result shuffling	open	10	TQC-10390	Simulation	Story	Distributed calculation		1.4
TQC-10393	API Authentication	open	8		Platform	Story	Public API		1.4
TQC-10394	Master Data API	open	14		Datastore	Story	Public API		1.4
TQC-10395	Simulation API	open	16		Simulation	Story	Public API		1.4
TQC-10396	Workflow API	open	12		Workflow	Story	Public API		1.4
TQC-10397	API Usage Monitoring	open	10		Platform	Story	Public API		1.4
TQC-10398	Workbook API	open	12		Analytics	Story	Public API		1.4
TQC-10399	Result Cache	open	8		Datastore	Story	Incremental Queries		1.4
TQC-10400	Sticky Sessions	open	10		Platform	Story	Incremental Queries		1.4
TQC-10401	Context Model	open	12		Analytics	Story	Incremental Queries		1.4
TQC-10402	Cache Invalidation	open	8	TQC-10399	Datastore	Story	Incremental Queries		1.4
TQC-10403	Data Merge	open	4	TQC-10401+TQC-10399	Frontend	Story	Incremental Queries		1.4
TQC-10404	Full reload	open	4	TQC-10403	Frontend	Story	Incremental Queries		1.4
TQC-10405	3D environment	open	20		Frontend	Story	VR visualization		1.4
TQC-10406	3D charts	open	14		Frontend	Story	VR visualization		1.4
TQC-10407	VR interaction module	open	20		Frontend	Story	VR visualization		1.4
TQC-10408	Voice control	open	18		Frontend	Story	VR visualization		1.4
TQC-10409	Subsecond queries	open	10	TQC-10403+TQC-10392	Platform	Story	VR visualization		1.4
TQC-10410	VR flux	open	10	TQC-10352+TQC-10407	Analytics	Story	VR visualization		1.4
TQC-10411	Datastore Introspection	open	4		Datastore	Story	Service Introspection		1.4
TQC-10412	Simulation Introspection	open	4		Simulation	Story	Service Introspection		1.4
TQC-10413	Analytics Introspection	open	4		Analytics	Story	Service Introspection		1.4
TQC-10414	Workflow Introspection	open	4		Workflow	Story	Service Introspection		1.4
TQC-10415	Provide Introspection Port	open	2		Platform	Story	Service Introspection		1.4
TQC-10416							APM Instrumentation
TQC-10417							APM Instrumentation
TQC-10418							APM Instrumentation
TQC-10419							APM Instrumentation
TQC-10420							APM Instrumentation
TQC-10421							APM Instrumentation
TQC-10422							Implicit Personalization
TQC-10423							Implicit Personalization
TQC-10424							Implicit Personalization
TQC-10425							Implicit Personalization
TQC-10426							Implicit Personalization
TQC-10427							Implicit Personalization
TQC-10428							Implicit Personalization
TQC-10429							Implicit Personalization
TQC-10430							Implicit Personalization
TQC-10431							Backend Performance
TQC-10432							Backend Performance
TQC-10433							Backend Performance
TQC-10434							Backend Performance
TQC-10435							Backend Performance
TQC-10436							Backend Performance
TQC-10437							Backend Performance
TQC-10438							Fisheye Navigation
TQC-10439							Fisheye Navigation
TQC-10440							Fisheye Navigation
TQC-10441							Fisheye Navigation
TQC-10442							Fisheye Navigation
TQC-10443							Fisheye Navigation
TQC-10444							Helix Charts
TQC-10445							Helix Charts
TQC-10446							Helix Charts
TQC-10447							Helix Charts
TQC-10448							Helix Charts
TQC-10449							Helix Charts
TQC-10450							Helix Charts
TQC-10451							Entity recognition
TQC-10452							Entity recognition
TQC-10453							Entity recognition
TQC-10454							Entity recognition
TQC-10455							Entity recognition
TQC-10456							Entity recognition
TQC-10457							Entity recognition
TQC-10458							Alexa support
TQC-10459							Alexa support
TQC-10460							Alexa support
TQC-10461							Alexa support
TQC-10462							Alexa support
TQC-10463							Alexa support
TQC-10464							Alexa support
TQC-10465							Snapshot store
TQC-10466							Snapshot store
TQC-10467							Snapshot store
TQC-10468							Snapshot store
TQC-10469							Snapshot store
TQC-10470							Snapshot store
TQC-10471							Snapshot store
TQC-10472							Usage Analytics
TQC-10473							Usage Analytics
TQC-10474							Usage Analytics
TQC-10475							Usage Analytics
TQC-10476							Usage Analytics
TQC-10477							Usage Analytics
TQC-10478							Usage Analytics
TQC-10479							Usage Analytics
TQC-10480
TQC-10481
TQC-10482
TQC-10483
TQC-10484
TQC-10485
TQC-10486
TQC-10487
TQC-10488
TQC-10489
TQC-10490
TQC-10491
TQC-10492
TQC-10493
TQC-10494
TQC-10495
TQC-10496
TQC-10497
TQC-10498
TQC-10499
TQC-10500
TQC-10501
TQC-10502
TQC-10503
TQC-10504
TQC-10505
TQC-10506
TQC-10507
TQC-10508
TQC-10509
TQC-10510
TQC-10511
TQC-10512
TQC-10513
TQC-10514
TQC-10515
TQC-10516
TQC-10517
TQC-10518
TQC-10519
TQC-10520
TQC-10521
TQC-10522
TQC-10523
TQC-10524
TQC-10525
TQC-10526
TQC-10527
TQC-10528
TQC-10529
TQC-10530
TQC-10531
TQC-10532
TQC-10533
TQC-10534
TQC-10535
TQC-10536
TQC-10537
TQC-10538
TQC-10539
TQC-10540
TQC-10541
TQC-10542
TQC-10543
TQC-10544
TQC-10545
TQC-10546
TQC-10547
TQC-10548
TQC-10549
TQC-10550
TQC-10551
TQC-10552

## Bugs
jira:bug	core:name	jira:status	jira:team	jira:sprint	jira:release
BUG-688	Flux Distortion	open	Datastore	2020-05	1.2
BUG-689	Unstable Time Dilatation	closed	Simulation	2020-03	1.2
BUG-690	Hubble Orbit Oscillation	in progress	Platform	2020-05	1.2
BUG-690	Quantum Leaks	in validation	Datastore	2020-05	1.2